## coverpage
Results achievable through programmed activity against HAC targets
The current programmed targets (column G) are based on the number of beneficiaries that will be reached under existing partnerships. This does not represent delivery to date, but what is achievable with existing resources.
| CCC | HAC | HAC target | Workplan target | Current programmed target | Current shortfall | Progress to target
Education | E2. Children including preschool age children, girls, and other excluded children, access quality education opportunities | School-aged children in affected areas in schools/learning programmes | 35530 |  | 23700 | 11830 | 66.7%
| E3. Safe and secure learning environments that promote the protection and well-being of learners is established | Safe and secure learning environments that promote the protection and well-being of learners is established | 200 |  | 14 | 186 | 7%
| E4. Psychosocial and health services for children and teachers is integrated in educational response | Children with access to psychosocial support in education programmes | 32720 |  | 9853 | 22867 | 30.11%
| E5 Adolescents, young children and caregivers access appropriate life skills programmes ; information about the emergency; and educational options for those who have missed out on schooling, especially adolescents | Children and adolescents benefitting from non-formal and informal educational services | 32720 |  | 16178 | 16542 | 49.44%
WASH | W2 Children and women access sufficient water of appropriate quality and quantity for drinking, cooking and maintaining personal hygiene | EAP provided with access to drinking and domestic water | 105000 |  | 27050 | 77950 | 25.76%
| W3. Children and women access toilets and washing facilities that are culturally appropriate, secure, and sanitary, and are user friendly and gender appropriate | EAP provided with access to soap and other hygiene items | 105000 |  | 44625 | 60375 | 42.5%
|  | EAP with access to appropriately designed toilets and sanitation services | 105000 |  | 4500 | 100500 | 4.286%
| W4. Children and women receive critical WASH related information to prevent child illness, especially diarrhea | Population having access to hygiene promotion messages | NA | 105000 | 8374 | 96626 | 7.975%
| W5. Children access safe water, sanitation and hygiene facilities in their learning environment | Children access safe water, sanitation and hygiene facilities in their learning environment and in child friendly spaces | 26100 |  | 1124 | 24976 | 4.307%
Health | H2. Children and women access life saving interventions through population-based/community-based activities e.g. campaigns and child health days | Children 9 months to 15 years vaccinated against measles | 74000 |  | 74000 | 0 | 100%
|  | Vitamin A supplementation (6 months to 15 years) | 74000 |  | 74000 | 0 | 100%
| H3. Children, women, and adolescents equitably access essential health services with sustained coverage of high impact preventive and curative interventions | No HAC target | NA | 81000 | 16155 | 81000 | 19.94%
| H4 Women and children access behaviour change communication interventions towards improving health care and feeding practices | No HAC target | NA | 27000 | 0 | 27000 | 0%
Nutrition | N4. Children and women access micronutrients from fortified foods, supplements, or multiple-micronutrient preparations | Children u5 receiving multi-micronutrient supplementation | 50000 |  | 60000 | -10000 | 120%
|  | PLWs receiving micronutrient supplementation | 8900 |  | 20000 | -11100 | 224.7%
| N2. Timely nutritional assessment and surveillance systems are established and/or reinforced | No HAC target | NA | 60000 | 60000 | 0 | 100%
| N3. Children and women with acute malnutrition access appropriate acute malnutrition management | Women having access to IYCF Services | NA | 40 | 0 | 40 | 0%
| N6: Children and women access relevant information about nutrition programme activities | No HAC target | NA | 27000 | 27000 | 0 | 100%
Child Protection | C2: Monitoring and reporting of grave violations and other serious protection concerns regarding children and women are undertaken and systematically trigger response (including advocacy) | No HAC target | NA | TBD | 0
| C3: Key child protection mechanisms are strengthened in emergency-affected areas | No HAC target | NA | 25 | 0 | 25 | 0%
| C4: Separation of children from families is prevented and addressed and family-based care is promoted. | No HAC target | NA | 1500 | 0 | 1500 | 0%
| C5: Violence, exploitation and abuse of children and women, including GBV, are prevented and addressed. | No HAC target | NA | 11000 | 2441 | 8559 | 22.19%
| C6: Psychosocial support is provided to children and their caregivers. | Children with access to psychosocial support services | 74000 |  | 68884 | 5116 | 93.09%
| C8: The use of landmines and other indiscriminate or illicit weapons by state and non-state actors is prevented, and their impact is addressed. | No HAC target | NA | 24000 | 24600 | -600 | 102.5%

## HAC PCA tracking
| CCC | HAC | HAC target | Partner | PCA # | Activity | Location | PCA funds | Donor | PBA | Start date | End date | Pipeline | Active | Complete | Target beneficiares non-HAC | Target beneficiaries HAC | Sum targetted by PCAs | Sum target pending PCAs | Gap between PCAs and HAC | Reached | Gap between PCA target and reached | Gap between HAC and reached
Education Education Education Education Education | E2. Children including preschool age children, girls, and other excluded children, access quality education opportunities | HAC1 - # in learning programmes | 35530 | Caritas | LEBA/2012/030 | BTS package (Parent Council fees, uniform, bag, stationery) and winter clothing | Bekaa, Mt Lebanon, North Lebanon | 1688755 |  | SC080883 SC100626 | 2012-10-01 | 2013-07-15 | 0 | 1 | 0 |  | 20000 | 23700 |  | 11830 | 11742 | 8258 | 20084
|  |  |  | Save the Children | LEBA/2012/029 | BTS package (Parent Council fees, uniform, bag, stationery) and winter clothing | North Lebanon | 625000 |  |  | 2012-09-01 | 2013-02-28 | 0 | 0 | 1 |  | 3700 |  |  |  | 3704 | -4
| E4. Psychosocial and health services for children and teachers is integrated in educational response | HAC2 - # access PSS in education | 32720 | IQRA | LEBA/2012/024 | Remedial classes and ALPs | Beirut, Bekaa, Mt Lebanon, Nabatiyeh, South Lebanon | 133172 |  |  | 2013-02-01 | 2014-07-31 | 0 | 1 | 0 |  | 1728 | 4958 |  | 27762 |  | 1728
|  |  |  | Amel | LEBA/2012/022 | Recreational activities with psychosocial activities | Bekaa | 109140 |  |  | 2012-08-01 | 2013-01-31 | 0 | 0 | 1 |  | 100 |  |  |  |  | 100
|  |  |  | AVSI | In process | PSS through Child Friendly Bus | South Lebanon | above |  |  | 2013-01-01 | 2013-06-30 | 1 | 0 | 0 | 73 |  |  | 900 |  |  | 0
|  |  |  | Mouvement Social | LEBA/2013/001 | Education, protection/ PSS, and life skills services | Bekaa, North Lebanon | 238259 |  | SM120452 | 2013-01-01 | 2013-06-30 | 0 | 1 | 0 |  | 230 |  |  |  |  | 230
|  |  |  | NRC | In process | PSS |  | 1587000 |  |  |  |  | 1 | 0 | 0 |  |  |  | 3260 |  |  | 0
|  |  |  | Save the Children | LEBA/2012/018 | PSS |  | 128445.5 |  |  | 2012-07-20 | 2013-01-31 | 0 | 0 | 1 |  | 900 |  |  |  |  | 900
|  |  |  | War Child Holland | In process | PSS | North Lebanon | above |  |  | 2013-03-01 | 2013-09-30 | 1 | 0 | 0 |  |  |  | 255 |  |  | 255
|  |  |  | Alpha | In process | PSS via ALP | Nabatiyeh | above |  |  | 2013-02-01 | 2013-07-31 | 1 | 0 | 0 |  |  |  | 480 |  |  | 480
|  |  |  | SAWA | LEBA/2013/002 | Traveling theatre for PSS | Bekaa | 275470.5 |  |  | 2013-01-01 | 2013-06-30 | 0 | 1 | 0 |  | 2000 |  |  |  |  | 2000
| E5 Adolescents, young children and caregivers access appropriate life skills programmes ; information about the emergency; and educational options for those who have missed out on schooling, especially adolescents | HAC3 # informal and non-formal education | 32720 | MADA | LEBA/2012/026 | Summer camps with CFSs and life skills | North Lebanon | above |  |  | 2013-05-01 | 2014-04-30 | 0 | 0 | 0 |  |  | 9040 | 0 | 7138 |  | 0
|  |  |  | AVSI | In process | Provide remedial classes to identified children | South Lebanon | 256291 |  |  | 2013-01-01 | 2013-06-30 | 1 | 0 | 0 |  |  |  | 473 |  |  | 0
|  |  |  | IQRA | LEBA/2012/024 | Provide remedial classes to identified children | Beirut, Bekaa, Mt Lebanon, Nabatiyeh, South Lebanon | above |  |  | 2013-02-01 | 2014-07-31 | 0 | 1 | 0 |  | 5184 |  |  |  |  | 5184
|  |  |  | Mouvement Social | LEBA/2013/001 | Provide remedial classes to identified children | Bekaa, North Lebanon | above |  | SM120452 | 2013-01-01 | 2013-06-30 | 0 | 1 | 0 |  | 950 |  |  |  |  | 950
|  |  |  | NRC | In process | Provide remedial classes to identified children |  | above |  |  |  |  | 1 | 0 | 0 |  |  |  | 500 |  |  | 0
|  |  |  | SAWA | LEBA/2013/002 | Provide remedial classes to identified children | Bekaa | above |  |  | 2013-01-01 | 2013-06-30 | 0 | 1 | 0 |  | 300 |  |  |  |  | 300
|  |  |  | War Child Holland | In process | Provide remedial classes to identified children | North Lebanon | 741082 |  |  | 2013-03-01 | 2013-09-30 | 1 | 0 | 0 |  |  |  | 1650 |  |  | 1650
|  |  |  | Relief International | In process | Provide remedial classes to identified children | North Lebanon and Mount Lebanon |  |  |  | 2013-02-01 | 2013-08-31 | 1 | 0 | 0 |  |  |  | 800 |  |  | 800
|  |  |  | Alpha | In process | Provide remedial classes to identified children | Nabatiyeh | 100000 |  |  | 2013-02-01 | 2013-07-31 | 1 | 0 | 0 |  |  |  | 480
|  |  |  | Save the Children | LEBA/2012/029 | Provide remedial classes to identified children | North Lebanon | above |  |  | 2012-09-01 | 2013-02-28 | 0 | 0 | 1 |  | 1000 |  |  |  |  | 1000
|  |  |  | MADA | LEBA/2012/026 | Remedial classes | North Lebanon | above |  |  | 2013-05-01 | 2014-04-30 | 0 | 0 | 0 |  |  |  | 500 |  |  | 500
|  |  |  | Amel | LEBA/2012/022 | ALP | Bekaa | above |  |  | 2012-08-01 | 2013-01-31 | 0 | 0 | 1 | 135 | 200 |  |  |  |  | 200
|  |  |  | Save the Children | LEBA/2012/018 | ALP |  | above |  |  | 2012-07-20 | 2013-01-31 |  |  |  |  | 150
|  |  |  | Save the Children | LEBA/2012/029 | ALP for out-of-school children | North Lebanon | above |  |  | 2012-09-01 | 2013-04-30 | 0 | 1 | 0 |  | 450 |  |  |  |  | 450
|  |  |  | War Child Holland | In process | ALP | North Lebanon | above |  |  | 2013-03-01 | 2013-09-30 | 1 | 0 | 0 |  |  |  | 255 |  |  | 255
|  |  |  | Alpha | In process | ALP | Nabatiyeh | above |  |  | 2013-02-01 | 2013-07-31 | 1 | 0 | 0 |  |  |  | 480 |  |  | 480
|  |  |  | NRC | In process | Implement ALP for out of school children | South Lebanon | above |  |  | 2013-01-01 | 2013-10-31 | 1 | 0 | 0 |  |  |  | 2000 |  |  | 0
|  |  |  | IQRA | LEBA/2012/024 | Implement ALP for out of school children | Beirut, Bekaa, Mt Lebanon, Nabatiyeh, South Lebanon | above |  |  | 2013-02-01 | 2014-07-31 | 0 | 1 | 0 |  | 576 |  |  |  |  | 576
|  |  |  | Mouvement Social | LEBA/2013/001 | Implement ALP for out of school children | Bekaa, North Lebanon | above |  |  | 2013-01-01 | 2013-06-30 | 0 | 1 | 0 |  | 230 |  |  |  |  | 230
| E3. Safe and secure learning environments that promote the protection and well-being of learners is established | HAC4 - # safe schools | 200 |  |  | Comprehensive needs assessment of schools for infrastructure, WASH and winter needs | [6 empty] | 0 | 0 | 0 |  |  | 0 |  | 176
|  |  |  | War Child Holland | In process | Provide schools with minor infrastructural improvements and basic educational supplies |  | tbc |  |  |  |  | 1 | 0 | 0 |  |  | 0 | 14
|  |  |  | Relief International | In process | Provide schools with minor infrastructural improvements and basic educational supplies |  | tbc |  |  |  |  | 1 | 0 | 0 |  |  | 0
[6 empty] | Provision of fuel for heating in schools | Bekaa, North | [5 empty] | 0 | 0 | 0 |  |  | 86 |  |  |  | 86
|  |  |  | Balamand University | LEBA/2012/033 | School Health Coordinators/additional social workers actively follow up on enrolment/retention throughout the school year (24,000 Syrian students) Train school staff on rapid emergency response in education | Bekaa | 321052 |  |  | 2012-11-01 | 2013-06-30 | 0 | 1 | 0 | 65 | [5 empty] | 65
[7 empty] | North |  |  |  | 2012-11-01 | 2013-06-30 | 0 | 1 | 0 | 39 | [5 empty] | 39
[7 empty] | Mount Lebanon |  |  |  | 2012-11-01 | 2013-06-30 | 0 | 1 | 0 | 48 | [5 empty] | 48
[7 empty] | Beirut |  |  |  | 2012-11-01 | 2013-06-30 | 0 | 1 | 0 | 20 | [5 empty] | 20
[7 empty] | South |  |  |  | 2012-11-01 | 2013-06-30 | 0 | 1 | 0 | 28 | [5 empty] | 28
|  |  |  | Save the Children | LEBA/2012/018 | Conduct training sessions on positive discipline and active learning methods for parents, teachers and administrators. |  | above |  |  | 2012-07-20 | 2013-01-31 | 0 | 0 | 1 | 640 | 5 |  |  |  |  | 950
|  |  |  | Save the Children | LEBA/2012/029 |  |  | above |  |  | 2012-09-01 | 2013-04-30 |  |  |  | 950 | 5
|  |  |  | IQRA | LEBA/2012/024 |  |  | above |  |  | 2013-02-01 | 2014-07-31 | 0 | 1 | 0 | 1296 | [5 empty] | 1296
|  |  |  | NRC | In process |  |  | above |  |  | 2013-01-01 | 2013-10-31 | 1 | 0 | 0 | 1296
|  |  |  | CERD | In process |  |  | 200000 |  |  |  |  | 1 | 0 | 0
|  |  |  | SAWA | LEBA/2013/002 |  | Bekaa | above |  |  | 2013-01-01 | 2013-06-30 | 0 | 1 | 0 | 1539
|  |  |  | AVSI | In process |  |  | above |  |  | 2013-01-01 | 2013-06-30 | 1 | 0 | 0 | 106
|  |  |  | MADA | LEBA/2012/026 |  | North Lebanon | above |  |  | 2013-05-01 | 2014-04-30 | 0 | 0 | 0 | 350
WASH WASH WASH | W2 Children and women access sufficient water of appropriate quality and quantity for drinking, cooking and maintaining personal hygiene | HAC1 EAP provided water access | 105000 | ACF | LEBA/2012/021 | Distribution of water storage tanks |  | 339033 |  |  | 2013-02-01 | 2013-08-01 | 0 | 1 | 0 |  | 3500 | 27050 |  | 77950
|  |  |  | CISP | LEBA/2012/32 | Distribution of water storage tanks |  | 399398.32 |  |  | 2012-12-01 | 2013-05-31 | 0 | 1 | 0 |  | 300
|  |  |  | PU- AMI | LEBA/2012/31 | Distribution of water storage tanks and vouchers |  | 400000 |  |  | 2012-11-01 | 2013-04-30 | 0 | 1 | 0 |  | 1000
|  |  |  | ACF | LEBA/2012/021 | Water trucking and vouchers |  | above |  |  | 2013-02-01 | 2013-08-01 | 0 | 1 | 0 |  | 12250
[6 empty] | WASH assessments | [6 empty] | 0 | 0 | 0
|  |  |  | ACF | LEBA/2012/021 | Water Treatment (filters, aquatab, etc) |  | above |  |  | 2013-02-01 | 2013-08-01 | 0 | 1 | 0 |  | 7500
|  |  |  | PU- AMI | LEBA/2012/31 | Water Treatment (filters, aquatab, etc) |  | above |  |  | 2012-11-01 | 2013-04-30 | 0 | 1 | 0 |  | 2500
[6 empty] | Repair/construction of small scale piped systems | [6 empty] | 0 | 0 | 0
[6 empty] | Distribution of NFI (buckets, jcs) | [6 empty] | 0 | 0 | 0
| W3. Children and women access toilets and washing facilities that are culturally appropriate, secure, and sanitary, and are user friendly and gender appropriate | HAC2 EAP provided soap and hygiene items | 105000 | DRC | LEBA/2012/025 | Winterization baby kits |  | 211392 |  |  | 2012-01-01 | 2012-11-30 | 0 | 0 | 1 |  | 3800 | 44625 |  | 60375
[6 empty] | Winterization hygiene kits |  | above |  |  | 2012-01-01 | 2012-11-30 | 0 | 0 | 1 |  | 28725
|  |  |  | PU- AMI | LEBA/2012/31 | Winterization hygiene kits |  | above |  |  | 2012-11-01 | 2013-04-30 | 0 | 1 | 0 |  | 5000
|  |  |  | UNRWA |  | Winterization baby kits | [6 empty] | 0 | 0 | 0 |  | 1000
[6 empty] | Winterization hygiene kits | [6 empty] | 0 | 0 | 0 |  | 4000
|  |  |  | Medair |  | Winterization hygiene kits | [6 empty] | 0 | 0 | 0 |  | 600
|  |  |  | CISP | LEBA/2012/32 | Hygiene kits |  | above |  |  | 2012-12-01 | 2013-05-31 | 0 | 1 | 0 |  | 1500
|  | HAC3 EAP provided toilets and sanitation | 105000 | ACF | LEBA/2012/021 | Desludging of existing latrines |  | above |  |  | 2013-02-01 | 2013-08-01 | 0 | 1 | 0 |  | 1500 | 4500 |  | 100500
[6 empty] | Rehab of latrines/toilets |  | above |  |  | 2013-02-01 | 2013-08-01 | 0 | 1 | 0 |  | 1250
|  |  |  | PU- AMI | LEBA/2012/31 |  |  | above |  |  | 2012-11-01 | 2013-04-30 | 0 | 1 | 0 |  | 1000
|  |  |  | CISP | LEBA/2012/32 | Maintenance of toilets |  | above |  |  | 2012-12-01 | 2013-05-31 | 0 | 1 | 0 |  | 750
[6 empty] | Construction of new latrines/toliets | [6 empty] | 0 | 0 | 0
[6 empty] | Provision of handwashing facilities | [6 empty] | 0 | 0 | 0
| W4. Children and women receive critical WASH related information to prevent child illness, especially diarrhea | Population having access to hygiene promotion messages | 105000 | ACF | LEBA/2012/021 | Hygiene Promotion & Education |  | above |  |  | 2013-02-01 | 2013-08-01 | 0 | 1 | 0 |  | 3500 | 3500 |  | 96626
|  |  |  | CISP | LEBA/2012/32 |  |  | above |  |  | 2012-12-01 | 2013-05-31 | 0 | 1 | 0 | 30 communities, 4 schools | 1124 | 1124
|  |  |  | PU- AMI | LEBA/2012/31 |  |  | above |  |  | 2012-11-01 | 2013-04-30 | 0 | 1 | 0 | 750 households | 3750 | 3750
| W5. Children access safe water, sanitation and hygiene facilities in their learning environment | HAC4, 5 & 6 Children access safe water, sanitation and hygiene facilities in their learning environment and in child friendly spaces | 26100 |  |  | Water Trucking | [6 empty] | 0 | 0 | 0 |  |  | 1124 |  | 24976
[6 empty] | Water Storage | [6 empty] | 0 | 0 | 0
[6 empty] | Hygiene Promotion & Education | [6 empty] | 0 | 0 | 0
|  |  |  | CISP | LEBA/2012/32 | Maintenance of sanitation facilities in schools |  | above |  |  | 2012-12-01 | 2013-05-31 | 0 | 1 | 0 | 4 schools | 1124
|  |  |  | ACF | LEBA/2012/021 | Provision of sanitation facilities |  | above |  |  | 2013-02-01 | 2013-08-01 | 0 | 1 | 0
Health and Nutrition Health and Nutrition Health and Nutrition | H2. Children and women access life saving interventions through population-based/community-based activities e.g. campaigns and child health days | HAC1 Children 9 months to 15 years vaccinated against measles | 74000 | Ministry of Public Health |  | Measles immunization |  |  |  |  | 2013-01-21 | 2013-02-09 | 0 | 0 | 1 |  | 74000 | 74000 |  | 0
|  | HAC 2 Vitamin A supplementation for children 6 months to 15 years |  |  |  | Vitamin A suppliementation |  |  |  |  | 2013-01-21 | 2013-02-09 | 0 | 0 | 1
|  | No HAC target |  |  |  | Polio immunization |  |  |  |  | 2013-01-21 | 2013-02-09 | 0 | 0 | 1
|  |  |  | Beyond | LEBA/2013/03 | Technical support for vaccination activities |  | 173122 |  |  | 2013-01-21 | 2013-02-09 | 0 | 0 | 1
| H3. Children, women, and adolescents equitably access essential health services with sustained coverage of high impact preventive and curative interventions | No HAC target | 0 | Save the Children | In process | Provide MoH and NGO PHCs with essential life-saving drugs, health supplies, emergency kits and obstetrical kits according to needs identified | Zahle (Bar Elias and Qob Elias) | 63060 |  |  | 2013-02-04 | 2013-03-16 | 1 | 0 | 0 | 2 |  |  | 16155
| H4 Women and children access behaviour change communication interventions towards improving health care and feeding practices | No HAC target | 0 |  |  | Train school health educators and social workers involved in the “One School for All Initiative” on designing, planning, implementing and monitoring of health awareness sessions for children’s caregivers. Special attention paid to hygiene promotion | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0
| N2. Timely nutritional assessment and surveillance systems are established and/or reinforced | No HAC target | 0 | IOCC | In process | Nutritional assessment and surveillance systems established and/or reinforced | Bekaa, North, South and Mount Lebanon | 242772 |  |  |  |  | 1 | 0 | 0 | 60000 |  |  | 60000 | 0
| N3. Children and women with acute malnutrition access appropriate acute malnutrition management | Women having access to IYCF Services | 0 | [9 empty] | 0 | 0 | 0 |  |  |  |  | 0
| N4. Children and women access micronutrients from fortified foods, supplements, or multiple-micronutrient preparations | Children u5 receiving multi-micronutrient supplementation | 50000 | IOCC | In process | Distribution of micronutrient supplements |  | above |  |  |  |  | 1 | 0 | 0 |  |  |  | 60000 | -10000 |  | -10000
|  | PLWs receiving micronutrient supplementation | 8900 | IOCC | In process | Distribution of micronutrient supplements |  | above |  |  |  |  | 1 | 0 | 0 |  |  |  | 20000 | -11100 |  | 8900
| N6: Children and women access relevant information about nutrition programme activities | No HAC target | 0 | IOCC | In process | Mother Support groups, awareness sessions with mothers and familes |  | above |  |  |  |  | 1 | 0 | 0 |  |  |  | 27000
Child Protection Child Protection Child Protection Child Protection | C5: Violence, exploitation and abuse of children and women, including GBV, are prevented and addressed. | No HAC target | 0 | IRC | LEBA/2012/36 | Support groups for adolescent girls | Bekaa (Aarsal, Zahle) North (Berqayel) | 395359 |  | SM120422 | 2012-12-17 | 2013-04-16 | 0 | 1 | 0 | 360 |  | 360 |  |  | 150
[6 empty] | Case management for girls surviving SGBV |  |  | US BPRM |  | 2012-12-17 | 2013-04-16 | 0 | 1 | 0 |  |  | 0
[6 empty] | Training on caring for child surviviors of sexual violence for IRC staff (15) |  |  |  |  | 2012-12-17 | 2013-04-16 | 0 | 1 | 0 |  |  | 0
[6 empty] | Training on caring for child surviviors of sexual violence for service providers (80) |  |  |  |  | 2012-12-17 | 2013-04-16 | 0 | 1 | 0 |  |  | 0
[6 empty] | Safety audits / focus groups (50) |  |  |  |  | 2012-12-17 | 2013-04-16 | 0 | 1 | 0 |  |  | 0
|  |  |  | Heartland Alliance | In process | GBV |  | 819620 | EU | SC130008 | 2013-03-15 | 2013-08-15 | 1 | 0 | 0 | 275 |  | 275
|  |  |  | Kafa | In process | GBV |  | 311950 | US BPRM | SM120422 | 2013-03-15 | 2013-08-15 | 1 | 0 | 0 | 1080 |  | 1080
|  |  |  | ABAAD | In process | GBV |  | 209003 | EU | SC130008 | 2013-03-15 | 2013-08-15 | 1 | 0 | 0 | 726 |  | 726
| C6: Psychosocial support is provided to children and their caregivers. | Number of children with access to psychosocial support services | 74000 | Arc An Ciel | LEBA/2012/034 | Reception/referral cases | Bekaa (Tanaayel, Zahle) North (Wadi Khaled, Helba) | 221965 | Global Thematic - Humanitarian | SM129906 | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 600 | 1200 |  | 3160
[6 empty] | Structured psychological support children |  |  |  |  | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 250
[6 empty] | Structured psychological support adults (250) |  |  |  |  | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 0
[6 empty] | Medical consultation |  |  |  |  | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 200
[6 empty] | Provision technical aids for children with disabilities |  |  |  |  | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 100
[6 empty] | Recreational activities (e.g. mobile circus) |  |  |  |  | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 420 |  |  |  | 200
[6 empty] | Parenting education sessions (80) |  |  |  |  | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 0
[6 empty] | Awareness sessions with children |  |  |  |  | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 520
[6 empty] | Awareness sessions with parents (80) |  |  |  |  | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 0
[6 empty] | Specialised sessions for children with disabilities |  |  |  |  | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 200
[6 empty] | Remedial classes |  |  |  |  | 2012-11-01 | 2013-05-08 | 0 | 1 | 0 |  | 100
|  |  |  | Amel | LEBA/2012/022 | Recreational activities (drawing, theatre, sports) | Bekaa (Kamed el Loz, El Ain) | above (in Education) |  |  | 2012-08-06 | 2013-01-31 | 0 | 0 | 1 |  | 200 | 200 | 900
[6 empty] | Individual support |  |  |  |  | 2012-08-06 | 2013-01-31 | 0 | 0 | 1
[6 empty] | Training staff |  |  |  |  | 2012-08-06 | 2013-01-31 | 0 | 0 | 1 | 26 | 0
|  |  |  | Amel | In process | PSS | Bekaa, Beirut | 305913 | UK | SM120365 | 2013-03-15 | 2013-09-15 | 1 | 0 | 0 | 726 | 1920 |  | 1920
|  |  |  | ACH | LEBA/2012/016 | Recreational activities | Bekaa (Hermel) | 26043 | CERF, SIDA | SM120222 SM120193 | 2012-06-11 | 2012-12-31 | 0 | 0 | 1 |  | 250 | 250
[6 empty] | Psychological first aid |  |  |  |  | 2012-06-11 | 2012-12-31 | 0 | 0 | 1
[6 empty] | Awareness raising sessions with parents |  |  |  |  | 2012-06-11 | 2012-12-31 | 0 | 0 | 1
|  |  |  | ACH | In process | PSS |  |  | US BPRM | SM120422 | 2013-03-15 | 2013-09-15 | 1 | 0 | 0 | 100 | 1740 |  | 1740
|  |  |  | AUB | In process | PSS |  | 149100 |  |  | 2013-03-15 | 2013-09-15 | 1 | 0 | 0 | 100
|  |  |  | AVSI | In process | PSS - mobile recreational activities | South | 179647 | UK | SM120365 | 2013-03-01 | 2013-08-31 | 1 | 0 | 0 | 175 |  |  | 1619
|  |  |  | Hoops | In process | PSS |  | 315802 |  |  | 2013-03-15 | 2013-09-15 | 1 | 0 | 0 | 1000 |  |  | 10000
|  |  |  | Intersos | In process | PSS | South | 379657 |  |  | 2013-03-15 | 2013-09-15 | 1 | 0 | 0 | 2050 |  |  | 4930
|  |  |  | Mercy Corps | LEBA/2012/020 | Janana mobile festival | Bekaa (Marj, Fakiha, Addous, Baalbeck) Wavel Camp | 355785 | EPF 1, SIDA, Global Thematic - Humanitarian | SIDA SM 120193 + SM 129906 + GE120010 | 2012-08-01 | 2013-04-30 | 0 | 1 | 0 |  | 720 | 2215
[6 empty] | Film screenings |  |  |  |  | 2012-08-01 | 2013-04-30 | 0 | 1 | 0 |  | 1070
[6 empty] | Interactive theatre |  |  |  |  | 2012-08-01 | 2013-04-30 | 0 | 1 | 0 |  | 150 |  | 2000 |  | 820
[6 empty] | Photo journalism workshop |  |  |  |  | 2012-08-01 | 2013-04-30 | 0 | 1 | 0 |  | 25
[6 empty] | Filmmaking workshop |  |  |  |  | 2012-08-01 | 2013-04-30 | 0 | 1 | 0 |  | 10
[6 empty] | Comfort for Kids and Moving Forward |  |  |  |  | 2012-08-01 | 2013-04-30 | 0 | 1 | 0 |  | 240
[6 empty] | Training of staff |  |  |  |  | 2012-08-01 | 2013-04-30 | 0 | 1 | 0
[6 empty] | Individual support |  |  |  |  | 2012-08-01 | 2013-04-30 | 0 | 1 | 0
[6 empty] | Mentoring of post-graduate psychology students |  |  |  |  | 2012-08-01 | 2013-04-30 | 0 | 1 | 0
[6 empty] | Support to parents |  |  |  |  | 2012-08-01 | 2013-04-30 | 0 | 1 | 0
|  |  |  | Mercy Corps | In process | PSS |  |  | UK | SM120365 |  |  | 1 | 0 | 0
|  |  |  | MOSA | RWP2012/13 |  |  |  | Swiss, UK, EU | SC120892, SM120365, SC130008 |  |  | 0 | 0 | 0 | 7500 families | 22500 | 22500
|  |  |  | Mouvement Social | LEBA/2013/01 | Recreational Activities | Bekaa, Beirut, North | 102070 | EC | SC130008 | 2013-01-07 | 2013-06-07 | 0 | 1 | 0 |  | 1200 | 1200
[6 empty] | Psychosocial support |  |  |  |  | 2013-01-07 | 2013-06-07 | 0 | 1 | 0
|  |  |  | Save the Children | LEBA/2012/029 | Recreational activities | North (Hisheh, Mahatta, Awadet, Machta, Hammoud, Bani Sakher, Amayer, Raim Khalaf) | 274875 |  | GE 120020 + SM120330 | 2012-09-01 | 2013-02-28 | 0 | 0 | 1 |  | 1500 | 1500
[6 empty] | Living skills groups |  |  |  |  | 2012-09-01 | 2013-02-28 | 0 | 0 | 1
[6 empty] | Training of staff |  |  |  |  | 2012-09-01 | 2013-02-28 | 0 | 0 | 1
[6 empty] | Individual support |  |  |  |  | 2012-09-01 | 2013-02-28 | 0 | 0 | 1
[6 empty] | Case management |  |  |  |  | 2012-09-01 | 2013-02-28 | 0 | 0 | 1
[6 empty] | Support to caregivers |  |  |  |  | 2012-09-01 | 2013-02-28 | 0 | 0 | 1
|  |  |  | SAWA | LEBA/2013/002 | Mobile recreational activities | Bekaa | 84837.5 | US BPRM | SM120422 | 2013-01-17 | 2013-06-17 | 0 | 1 | 0 |  | 2000 | 2000
|  |  |  | Sheild | In process | PSS |  | 108350 | UK | SM120365 |  |  | 1 | 0 | 0
|  |  |  | TdH-It | LEBA/2012/012 | Individual psychosocial support | Bekaa (Aarsal) | 113163 |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1 |  | 300 | 300
[6 empty] | Recreational activities |  |  |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1 |  |  |  | 3000
[6 empty] | Training of staff |  |  |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1
[6 empty] | Case management |  |  |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1
[6 empty] | Support to caregivers |  |  |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1
|  |  |  | TdH-It | In process | PSS | South | 255190 | UK | SM120365 | 2013-03-15 | 2013-09-15 | 1 | 0 | 0 | 1000 |  |  | 3260
|  |  |  | TdH-Lausanne | In process | PSS | South | 278564 |  |  | 2013-04-01 | 2013-09-30 |  |  | 0 | 1500 |  |  | 4800
|  |  |  | War Child Holland | LEBA/2012/011 | Recreational activities | North (Halba, Wadi Nahle, Bourl el Arab, Balanet el Haysa, Al Kawashra, Bedaowi) | 126196 |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1 |  | 1350 | 1350 | 2000
[6 empty] | Living skills groups |  |  |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1
[6 empty] | Training of staff |  |  |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1
[6 empty] | Individual support |  |  |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1
[6 empty] | Case management |  |  |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1
[6 empty] | Support to caregivers |  |  |  |  | 2012-05-31 | 2012-11-30 | 0 | 0 | 1
|  |  |  | War Child Holland | In process | PSS | North | 417387 | CIDA | SM120452 | 2013-03-15 | 2013-09-13 | 1 | 0 | 0 | 210 |  |  | 1956
| C8: The use of landmines and other indiscriminate or illicit weapons by state and non-state actors is prevented, and their impact is addressed. | No HAC target | 0 |  |  | MRE knowledge, Awareness and Practices survey targeting communities living in infected areas – 1200 children from the age group 6-18 | Bekaa, South | [5 empty] | 0 | 0 | 0
[6 empty] | Deliver refresher training for 360 MRE activists from MRE steering committee members, schools including health counsellors, teachers, SDCs and humanitarian actors in the selected areas | [6 empty] | 0 | 0 | 0
[6 empty] | Deliver 500 MRE awareness session in at least 200 primary and elementary public schools targeting children from 5-14 and 100 secondary public schools targeting youth from 14 to 18 years old and in community based organizations to reach parents and out of school children | [6 empty] | 0 | 0 | 0
[6 empty] | Review existing MRE public information material and produce updated version to cover the knowledge gap identified through the KAP study | [6 empty] | 0 | 0 | 0
|  |  |  | Save the Children | LEBA/2012/018 | Mine risk education |  | above |  |  | 2012-07-01 | 2013-01-31 |  |  |  |  | 300 | 300
|  |  |  | Save the Children | LEBA/2012/029 | Mine risk education |  | above |  |  | 2012-09-01 | 2013-02-28 |  |  |  |  | 300 | 300
|  |  |  | LMAC | In process | Mine risk education |  | 128935 | Italy | SM120330 |  |  | 1 | 0 | 0 |  |  |  | 24000
| C2: Monitoring and reporting of grave violations and other serious protection concerns regarding children and women are undertaken and systematically trigger response (including advocacy). | No HAC target | 0 |  |  | Undertake training and technical assistance on MRM through ongoing partnership and established MRM IMS | [6 empty] | 0 | 0 | 0
| C3: Key child protection mechanisms are strengthened in emergency-affected areas | No HAC target | 0 |  |  | Support local implementation of standardized tools and protocols for handling child protection cases in target areas | [6 empty] | 0 | 0 | 0
[6 empty] | Design and deliver multidisciplinary training on child protection for professionals and paraprofessionals caregivers | [6 empty] | 0 | 0 | 0
[6 empty] | Establish and support community based child protection service delivery in targeted areas through CFS`s and SDCs (including temporary shelters for children at risk and victim of violence) | [6 empty] | 0 | 0 | 0
| C4: Separation of children from families is prevented and addressed and family-based care is promoted. | No HAC target | 0 |  |  | 1500 CP cases identified and supported through case management system (this includes UASC). | [6 empty] | 0 | 0 | 0
[6 empty] | Support family tracing and documention and provide temporary accommodation until reunification (if appropriate) is possible. | [6 empty] | 0 | 0 | 0
[6 empty] | UNICEF will support the establishment of an effective IA CP IMS and IDTR mechanism | [6 empty] | 0 | 0 | 0
Formulas:
Active = IF([Pipeline]=0,(IF(AND(TODAY()<[End date],[Start date]<TODAY()),1,0)),0)
Complete = IF(AND(TODAY()>[End date],[End date]>0),1,0)
Note on R3: redr: target 2,000, but have reported enroling 3,700
Note on D49: RRP4 target
Note on R72: redr: number for schools only, not communities
Note on T83: redr: Syrians only, actual beneficiaries will be much higher

## active and pipe
Row Labels | Max of Active | Max of Pipeline | Max of Complete
In process | 0 | 1 | 0
ACH | 0 | 1 | 0
Alpha | 0 | 1 | 0
Amel | 0 | 1 | 0
AVSI | 0 | 1 | 0
CERD | 0 | 1 | 0
IOCC | 0 | 1 | 0
Mercy Corps | 0 | 1 | 0
NRC | 0 | 1 | 0
Relief International | 0 | 1 | 0
Save the Children | 0 | 1 | 0
TdH-It | 0 | 1 | 0
War Child Holland | 0 | 1 | 0
Heartland Alliance | 0 | 1 | 0
Kafa | 0 | 1 | 0
ABAAD | 0 | 1 | 0
AUB | 0 | 1 | 0
Hoops | 0 | 1 | 0
Intersos | 0 | 1 | 0
Sheild | 0 | 1 | 0
LMAC | 0 | 1 | 0
LEBA/2012/011 | 0 | 0 | 1
War Child Holland | 0 | 0 | 1
LEBA/2012/016 | 0 | 0 | 1
ACH | 0 | 0 | 1
LEBA/2012/018 | 0 | 0 | 1
Save the Children | 0 | 0 | 1
LEBA/2012/020 | 1 | 0 | 0
Mercy Corps | 1 | 0 | 0
LEBA/2012/021 | 1 | 0 | 0
ACF | 1 | 0 | 0
LEBA/2012/022 | 0 | 0 | 1
Amel | 0 | 0 | 1
LEBA/2012/024 | 1 | 0 | 0
IQRA | 1 | 0 | 0
LEBA/2012/025 | 0 | 0 | 1
DRC | 0 | 0 | 1
LEBA/2012/026 | 0 | 0 | 0
MADA | 0 | 0 | 0
LEBA/2012/029 | 0 | 0 | 0
Save the Children | 0 | 0 | 0
LEBA/2012/029 LEBA/2012/018 | 1 | 0 | 0
Save the Children | 1 | 0 | 0
LEBA/2012/030 | 1 | 0 | 0
Caritas | 1 | 0 | 0
LEBA/2012/033 | 1 | 0 | 0
Balamand University | 1 | 0 | 0
LEBA/2012/034 | 1 | 0 | 0
Arc An Ciel | 1 | 0 | 0
LEBA/2012/31 | 1 | 0 | 0
PU- AMI | 1 | 0 | 0
LEBA/2012/32 | 1 | 0 | 0
CISP | 1 | 0 | 0
LEBA/2012/36 | 1 | 0 | 0
IRC | 1 | 0 | 0
LEBA/2013/001 | 1 | 0 | 0
Mouvement Social | 1 | 0 | 0
LEBA/2013/002 | 1 | 0 | 0
SAWA | 1 | 0 | 0
LEBA/2013/01 | 1 | 0 | 0
Mouvement Social | 1 | 0 | 0
LEBA/2013/03 | 0 | 0 | 1
Beyond | 0 | 0 | 1
(blank) | 1 | 0 | 1
Medair | 0 | 0 | 0
Ministry of Public Health | 0 | 0 | 1
Save the Children | 1 | 0 | 0
UNRWA | 0 | 0 | 0
(blank) | 1 | 0 | 1
RWP2012/13 | 0 | 0 | 0
MOSA | 0 | 0 | 0
LEBA/2012/012 | 0 | 0 | 1
TdH-It | 0 | 0 | 1
Grand Total | 1 | 1 | 1